## Tabelle1
ID | Title | Priority | Planned In | Status | Created | Type | Linked Work Items | _polarion
SCC-13359 | SIS Dog Verklingung im Polarion kaputt | Medium |  | New | 44958.5507 | Bug Report |  | SCC_Polarion/SCC-13359
SCC-13186 | Anpassung Validierung SW | Medium |  | Open | 44956.7435 | Task | implements: SCC-12364 | SCC_Polarion/SCC-13186
SCC-13185 | Anpassung Dokument Sicherheitsfunktionen | Medium |  | Open | 44956.7433 | Task | implements: SCC-12364 | SCC_Polarion/SCC-13185
SCC-13184 | Vergleich der Dokumente | Medium |  | Open | 44956.6796 | Task | implements: SCC-13183 | SCC_Polarion/SCC-13184
SCC-13183 | Vergleich der Bedienkonzepte | Lowest |  | Accepted | 44956.6794 | User Story | specifies: SCC-13168, is implemented by: SCC-13184 | SCC_Polarion/SCC-13183
SCC-13182 | Überarbeitung nach Review und Freigabe | Medium |  | Open | 44956.6771 | Task | implements: SCC-13178 | SCC_Polarion/SCC-13182
SCC-13181 | Review | Medium |  | Open | 44956.6769 | Task | implements: SCC-13178 | SCC_Polarion/SCC-13181
SCC-13180 | Anpassung Dokumentation | Medium |  | Open | 44956.6768 | Task | implements: SCC-13178 | SCC_Polarion/SCC-13180
SCC-13179 | Meeting Abgleich der Bedienungen | Medium |  | Open | 44956.6766 | Task | implements: SCC-13178 | SCC_Polarion/SCC-13179
SCC-13178 | Abgleich Bedienung | Lowest |  | Accepted | 44956.6761 | User Story | specifies: SCC-13168, is implemented by: SCC-13179, is implemented by: SCC-13180, is implemented by: SCC-13181, is implemented by: SCC-13182 | SCC_Polarion/SCC-13178
SCC-13177 | Überarbeitung nach Review und Freigabe | Medium |  | Open | 44956.6709 | Task | implements: SCC-13167 | SCC_Polarion/SCC-13177
SCC-13176 | Review | Medium |  | Open | 44956.6707 | Task | implements: SCC-13167 | SCC_Polarion/SCC-13176
SCC-13175 | Anpassung Dokumentation | Medium |  | Open | 44956.6703 | Task | implements: SCC-13167 | SCC_Polarion/SCC-13175
SCC-13174 | Meeting Abgleich Farben | Medium |  | Open | 44956.6702 | Task | implements: SCC-13167 | SCC_Polarion/SCC-13174
SCC-13173 | Überarbeitung nach Review | Medium |  | Open | 44956.6698 | Task | implements: SCC-13169 | SCC_Polarion/SCC-13173
SCC-13172 | Review | Medium |  | Open | 44956.6695 | Task | implements: SCC-13169 | SCC_Polarion/SCC-13172
SCC-13171 | Anpassung Dokumentation | Medium |  | Open | 44956.6689 | Task | implements: SCC-13169 | SCC_Polarion/SCC-13171
SCC-13170 | Meeting Abgleich Symbolik | Medium |  | Open | 44956.6684 | Task | implements: SCC-13169 | SCC_Polarion/SCC-13170
SCC-13169 | Abgleich Symbole | Lowest |  | Accepted | 44956.6549 | User Story | specifies: SCC-13168, is implemented by: SCC-13170, is implemented by: SCC-13172, is implemented by: SCC-13173, is implemented by: SCC-13171 | SCC_Polarion/SCC-13169
SCC-13168 | Abgleich Bedienkonzept SCC und SCS | Highest |  | Accepted | 44956.6506 | Epic | is specified by: SCC-13167, is specified by: SCC-13169, is specified by: SCC-13178, is specified by: SCC-13183 | SCC_Polarion/SCC-13168
SCC-13167 | Farbkozept zwischen SCC und SCS abgleichen | Lowest |  | Accepted | 44956.6461 | User Story | specifies: SCC-13168, is related to: SCC-12513, is implemented by: SCC-13174, is implemented by: SCC-13176, is implemented by: SCC-13177, is implemented by: SCC-13175 | SCC_Polarion/SCC-13167
SCC-13166 | Joystick_activ wird nicht zurückgesetzt! | Medium |  | In Progress | 44956.5085 | Bug Report |  | SCC_Polarion/SCC-13166
SCC-13165 | magic numbers statt Anwenderkonstanten im yHoist01 | Medium |  | New | 44956.4876 | Bug Report |  | SCC_Polarion/SCC-13165
SCC-13164 | Kapitel in Bedienkonzept und Betriebsanleitung angleichen | Medium |  | Open | 44956.4181 | Task | implements: SCC-12957 | SCC_Polarion/SCC-13164
SCC-13122 | DataLogging | Lowest |  | New | 44953.3904 | Enhancement Request |  | SCC_Polarion/SCC-13122
SCC-13121 | Anleitung Schleppketten Auslegung | Lowest |  | New | 44951.415 | Enhancement Request |  | SCC_Polarion/SCC-13121
SCC-13109 | Einspeise Box 400V vorlage RBG | Lowest |  | New | 44951.422 | Enhancement Request |  | SCC_Polarion/SCC-13109
SCC-12960 | Überarbeitung nach Review und Freigabe | Medium |  | Open | 44950.3323 | Task | implements: SCC-12957 | SCC_Polarion/SCC-12960
SCC-12959 | Review | Medium |  | Open | 44950.332 | Task | implements: SCC-12957 | SCC_Polarion/SCC-12959
SCC-12958 | Überarbeitng des Dokumentes | Medium |  | Open | 44950.3318 | Task | implements: SCC-12957 | SCC_Polarion/SCC-12958
SCC-12957 | Betriebsanleitung an Ausführungsspez angleichen | Lowest |  | Accepted | 44950.3315 | User Story | specifies: SCC-12952, is implemented by: SCC-12958, is implemented by: SCC-12959, is implemented by: SCC-12960, is implemented by: SCC-13164 | SCC_Polarion/SCC-12957
SCC-12956 | Überarbeitung nach Review und Freigabe | Medium |  | Open | 44949.6942 | Task | implements: SCC-12953 | SCC_Polarion/SCC-12956
SCC-12955 | Review | Medium |  | Open | 44949.694 | Task | implements: SCC-12953 | SCC_Polarion/SCC-12955
SCC-12954 | fehlende Kapitel erstellen | Medium |  | Open | 44949.6938 | Task | implements: SCC-12953 | SCC_Polarion/SCC-12954
SCC-12953 | Schnittstelle und Remote Zugang / Fernwartung in Ausführungsspezifikation implementieren | Lowest |  | Accepted | 44949.6936 | User Story | specifies: SCC-12952, is implemented by: SCC-12954, is implemented by: SCC-12956, is implemented by: SCC-12955 | SCC_Polarion/SCC-12953
SCC-12952 | Abgleich GU-Angebotstext, Ausführungsspezifikation, Betriebsanleitung SCC / SCS | Highest |  | Accepted | 44949.6896 | Epic | is specified by: SCC-12953, is specified by: SCC-12957 | SCC_Polarion/SCC-12952
SCC-12725 | Sonderposition EP/AP Verarbeitung funktioniert nicht | Medium |  | New | 44945.7566 | Bug Report |  | SCC_Polarion/SCC-12725
SCC-12724 | Überarbeitung GU-Angebotstext | Lowest |  | Draft | 44945.7531 | User Story | specifies: SCC-1871 | SCC_Polarion/SCC-12724
SCC-12723 | SPS Komentare mit | Medium |  | Assigned to Submitter | 44945.6947 | Bug Report |  | SCC_Polarion/SCC-12723
SCC-12709 | Überarbeitung SCC - SCS Kommunikation | Lowest |  | New | 44943.4378 | Enhancement Request |  | SCC_Polarion/SCC-12709
SCC-12708 | HMI um Subkonfig erweitern | Medium |  | Assigned to Submitter | 44942.731 | Bug Report |  | SCC_Polarion/SCC-12708
SCC-12707 | Geschwindigkeitsauswahl auf Ebene Axis/SwrIf | Lowest |  | New | 44939.3259 | Enhancement Request |  | SCC_Polarion/SCC-12707
SCC-12685 | Green-, GentleDrive verfälscht Offset | Medium |  | New | 44938.373 | Bug Report |  | SCC_Polarion/SCC-12685
SCC-12684 | Ein-, Ausschalten Bedienort gibt VÜberwachung | Medium |  | New | 44938.3653 | Bug Report |  | SCC_Polarion/SCC-12684
SCC-12683 | InPosition- Prüfung im falschen Part | Medium |  | New | 44938.3631 | Bug Report |  | SCC_Polarion/SCC-12683
SCC-12682 | Stopp In Pos Bedämpfung für X | Medium |  | New | 44938.3394 | Bug Report |  | SCC_Polarion/SCC-12682
SCC-12681 | ElSwrIf tMototTurning keine Temp Variabel | Medium |  | New | 44938.3382 | Bug Report |  | SCC_Polarion/SCC-12681
SCC-12680 | Spitzfahrtvermeidung führt zu Schleichen | Medium |  | New | 44938.3371 | Bug Report |  | SCC_Polarion/SCC-12680
SCC-12635 | Simulation: Fehler 055_TimeoutAgree löst falsch aus | Medium |  | New | 44936.7186 | Bug Report |  | SCC_Polarion/SCC-12635
SCC-12634 | Testbetrieb wird zuende gefahren, auch wenn Zustimmtaster losgelassen wird | Medium |  | New | 44936.7055 | Bug Report |  | SCC_Polarion/SCC-12634
SCC-12633 | Cybersicherheit | Lowest | Sprint 3, SCC 2.108.0 | Draft | 44935.7357 | User Story | specifies: SCC-12109 | SCC_Polarion/SCC-12633
SCC-12631 | ePlan von 'Version 2.9' Hochziehen auf 'Plattform 2023' | Lowest |  | New | 44930.5422 | Enhancement Request | relates to: SCS-31068 | SCC_Polarion/SCC-12631
SCC-12544 | Safety Simulation Y-Bremsschütz nicht simuliert | Medium |  | In Progress | 44911.4638 | Bug Report |  | SCC_Polarion/SCC-12544
SCC-12543 | Doppel LAM | Highest |  | Draft | 44910.6304 | Epic |  | SCC_Polarion/SCC-12543
SCC-12540 | Spitzfahrt vmin anstatt PosLow | Medium |  | New | 44910.3393 | Bug Report |  | SCC_Polarion/SCC-12540
SCC-12539 | Überarbeitung und Freigabe: Neues Typical für Doppeltiefe erstellt | Medium |  | Open | 44909.7559 | Task | implements: SCC-12536 | SCC_Polarion/SCC-12539
SCC-12538 | Review: Neues Typical für Doppeltiefe erstellt | Medium |  | Open | 44909.7556 | Task | implements: SCC-12536 | SCC_Polarion/SCC-12538
SCC-12537 | Dokumentation erstellen: Neues Typical für Doppeltiefe erstellt | Medium |  | Open | 44909.7554 | Task | implements: SCC-12536 | SCC_Polarion/SCC-12537
SCC-12536 | Neues Typical für Doppeltiefe erstellt | Lowest |  | Draft | 44909.7456 | User Story | specifies: SCC-12535, is implemented by: SCC-12539, is implemented by: SCC-12538, is implemented by: SCC-12537 | SCC_Polarion/SCC-12536
SCC-12535 | Doppeltiefe | Highest |  | Accepted | 44909.7446 | Epic | is specified by: SCC-12536 | SCC_Polarion/SCC-12535
SCC-12534 | Ersatz SMS 2000 Standalone | Lowest |  | Draft | 44909.712 | User Story | specifies: SCC-11883, relates to: SCC-12357, is related to: SCC-9132 | SCC_Polarion/SCC-12534
SCC-12533 | Ersatz SMS 2000 mit MoviC | Lowest |  | Draft | 44909.7094 | User Story | specifies: SCC-11883, relates to: SCC-12357, is related to: SCC-9132 | SCC_Polarion/SCC-12533
SCC-12532 | Kickoff : Anleitung ePlan Macros | Medium |  | Open | 44909.4498 | Task | implements: SCC-10154 | SCC_Polarion/SCC-12532
SCC-12531 | Überarbeitung nach zweitem Review und Freigabe: Anleitung E-Plan Prozess | Medium |  | Open | 44909.4459 | Task | implements: SCC-10155 | SCC_Polarion/SCC-12531
SCC-12530 | Zweites Review: Anleitung E-Plan Prozess | Medium |  | Open | 44909.4456 | Task | implements: SCC-10155 | SCC_Polarion/SCC-12530
SCC-12529 | Überbrückung wird gehalten | Medium |  | In Progress | 44909.3928 | Bug Report | is related to: SCS-32028 | SCC_Polarion/SCC-12529
SCC-12528 | Überarbeitung nach Review: Review Schema | Medium |  | Open | 44907.2922 | Task | implements: SCC-12525 | SCC_Polarion/SCC-12528
SCC-12527 | Überprüfung der Daten: Review Schema | Medium |  | Open | 44907.291 | Task | implements: SCC-12525 | SCC_Polarion/SCC-12527
SCC-12526 | Funktionale Überprüfung: Review Schema | Medium |  | Open | 44907.2892 | Task | implements: SCC-12525 | SCC_Polarion/SCC-12526
SCC-12525 | Review Schema | Lowest | Sprint 2, Sprint 3, SCC 2.108.0 | Draft | 44907.2888 | User Story | specifies: SCC-2577, is implemented by: SCC-12527, is implemented by: SCC-12526, is implemented by: SCC-12528 | SCC_Polarion/SCC-12525
SCC-12517 | Überarbeitung nach Review: GU Angebotstext für Retrofit | Medium |  | Open | 44900.5865 | Task | implements: SCC-12514 | SCC_Polarion/SCC-12517
SCC-12516 | Review: GU Angebotstext für Retrofit | Medium |  | Open | 44900.5862 | Task | implements: SCC-12514 | SCC_Polarion/SCC-12516
SCC-12515 | Erstellen: GU Angebotstext für Retrofi | Medium |  | Open | 44900.5859 | Task | implements: SCC-12514 | SCC_Polarion/SCC-12515
SCC-12514 | GU Angebotstext für Retrofit | Lowest |  | Draft | 44900.5835 | User Story | specifies: SCC-1871, is implemented by: SCC-12515, is implemented by: SCC-12517, is implemented by: SCC-12516 | SCC_Polarion/SCC-12514
SCC-12512 | URL-Adressen für Kamera über Variable vorgeben | Lowest |  | Accepted | 44896.6116 | Enhancement Request | relates to: SCC-12510 | SCC_Polarion/SCC-12512
SCC-12511 | Design im 031_DurTest noch das alte | Medium |  | New | 44896.5931 | Bug Report |  | SCC_Polarion/SCC-12511
SCC-12510 | Button Z-Tiefe 2 in 030_OpTest | Lowest |  | Accepted | 44896.5626 | Enhancement Request | is related to: SCC-12512 | SCC_Polarion/SCC-12510
SCC-12509 | gefunden im Release 2.107: im Panel 020_OpMan - die X+/Y--Taste hat ne andere Hö... | Medium |  | New | 44896.5002 | Bug Report |  | SCC_Polarion/SCC-12509
SCC-12508 | Durchschalten der EP- und AP-Positionen im Panel | Medium |  | New | 44896.4558 | Bug Report |  | SCC_Polarion/SCC-12508
SCC-12498 | SCC Schnittstellesignalen über AS-AS zu SCS Anlagen sollten über einzelne Status UDT ausgetauscht werden | Medium |  | New | 44890.5496 | Bug Report |  | SCC_Polarion/SCC-12498
SCC-12448 | Bereichslängenfehler xChassisReadPos | Medium |  | New | 44881.3662 | Bug Report |  | SCC_Polarion/SCC-12448
SCC-12379 | Überarbeitung nach Review und Freigabe | Medium |  | Open | 44879.5478 | Task | implements: SCC-12376 | SCC_Polarion/SCC-12379
SCC-12378 | Review | Medium |  | Open | 44879.5476 | Task | implements: SCC-12376 | SCC_Polarion/SCC-12378
SCC-12377 | Erstellen | Medium |  | Open | 44879.5475 | Task | implements: SCC-12376 | SCC_Polarion/SCC-12377
SCC-12376 | Anpassung SW | Lowest |  | Accepted | 44879.5472 | User Story | specifies: SCC-12356, is implemented by: SCC-12379, is implemented by: SCC-12377, is implemented by: SCC-12378 | SCC_Polarion/SCC-12376
SCC-12375 | Überarbeitung nach Review und Freigabe | Medium |  | Open | 44879.5452 | Task | implements: SCC-12372 | SCC_Polarion/SCC-12375
SCC-12374 | Review | Medium |  | Open | 44879.5449 | Task | implements: SCC-12372 | SCC_Polarion/SCC-12374
SCC-12373 | Erstellen | Medium |  | Open | 44879.5448 | Task | implements: SCC-12372 | SCC_Polarion/SCC-12373
SCC-12372 | Anpassungen im Schema | Lowest |  | Accepted | 44879.5447 | User Story | specifies: SCC-12356, is implemented by: SCC-12374, is implemented by: SCC-12373, is implemented by: SCC-12375 | SCC_Polarion/SCC-12372
SCC-12371 | Anpassung nach Review und Freigabe | Medium |  | Open | 44879.5431 | Task | implements: SCC-12368 | SCC_Polarion/SCC-12371
SCC-12370 | Revew | Medium |  | In Progress | 44879.5429 | Task | implements: SCC-12368 | SCC_Polarion/SCC-12370
SCC-12368 | Anpassen Elm Subsysteme | Lowest | Sprint 3, SCC 2.108.0 | In Progress | 44879.5425 | User Story | specifies: SCC-12356, is implemented by: SCC-12371, is implemented by: SCC-12369, is implemented by: SCC-12370 | SCC_Polarion/SCC-12368
SCC-12367 | Überarbeitung nach Review und Freigabe | Medium |  | Open | 44879.5382 | Task | implements: SCC-12364 | SCC_Polarion/SCC-12367
SCC-12366 | Review | Medium |  | In Progress | 44879.538 | Task | implements: SCC-12364 | SCC_Polarion/SCC-12366
SCC-12364 | Anpassung Sicherheitskonzept | Lowest | Sprint 3, SCC 2.108.0 | Accepted | 44879.5375 | User Story | specifies: SCC-12356, is implemented by: SCC-13185, is implemented by: SCC-13186, is implemented by: SCC-12367, is implemented by: SCC-12365, is implemented by: SCC-12366 | SCC_Polarion/SCC-12364
SCC-12363 | Überarbeiten und Freigeben | Medium |  | Open | 44879.535 | Task | implements: SCC-12360 | SCC_Polarion/SCC-12363
SCC-12362 | Review | Medium |  | In Progress | 44879.5348 | Task | implements: SCC-12360 | SCC_Polarion/SCC-12362
SCC-12360 | Beschreibung Antriebskonzept | Lowest | Sprint 3, SCC 2.108.0 | Accepted | 44879.5343 | User Story | specifies: SCC-12356, is implemented by: SCC-12363, is implemented by: SCC-12362, is implemented by: SCC-12361 | SCC_Polarion/SCC-12360
SCC-12356 | Sichere Geschwindigkeit | Highest |  | In Progress | 44879.4792 | Epic | relates to: SCC-11883, is specified by: SCC-12376, is specified by: SCC-12372, is specified by: SCC-12360, is specified by: SCC-12364, is specified by: SCC-12368, is specified by: SCC-12357 | SCC_Polarion/SCC-12356
SCC-12355 | Eplan Aufbaupläne | Lowest |  | Accepted | 44875.585 | Enhancement Request |  | SCC_Polarion/SCC-12355
SCC-12354 | +11 +12 LAM Bedienung | Lowest |  | Accepted | 44875.5827 | Enhancement Request |  | SCC_Polarion/SCC-12354
SCC-12112 | Anleitung ePlan Macros: Implementation nach Review | Medium |  | Open | 44868.3957 | Task | implements: SCC-10154 | SCC_Polarion/SCC-12112
SCC-12111 | Anleitung ePlan Macros: Review | Medium |  | Open | 44868.3955 | Task | implements: SCC-10154 | SCC_Polarion/SCC-12111
SCC-12110 | Anleitung ePlan Macros: Erstellen | Medium |  | In Progress | 44868.3952 | Task | implements: SCC-10154 | SCC_Polarion/SCC-12110
SCC-12109 | TIA V18 | Highest |  | In Progress | 44867.5407 | Epic | is specified by: SCC-12633, is related to: SCC-7340, is related to: SCC-6713, is specified by: SCC-12518 | SCC_Polarion/SCC-12109
SCC-12108 | SCC im grösseren Kontext | Highest |  | Draft | 44867.4758 | Epic |  | SCC_Polarion/SCC-12108
SCC-12107 | PTC Mechanik | Highest |  | Draft | 44867.4716 | Epic | is related to: SCC-11861 | SCC_Polarion/SCC-12107
SCC-11883 | Neue Norm | Highest |  | In Progress | 44860.8836 | Epic | is related to: SCC-6697, is related to: SCC-9132, is related to: SCC-9220, is related to: SCC-9217, is related to: SCC-9214, is related to: SCC-9222, is related to: SCC-9218, is related to: SCC-9530, is related to: SCC-6698, is related to: SCC-6699, is related to: SCC-6696, is related to: SCC-6677, is related to: SCC-6701, is related to: SCC-6702, is related to: SCC-6700, is related to: SCC-6385, is related to: SCC-12356, is specified by: SCC-12533, is specified by: SCC-12534 | SCC_Polarion/SCC-11883
SCC-11865 | LR Telegramm in Standard einbauen | Lowest |  | Assigned to Submitter | 44860.4978 | Enhancement Request |  | SCC_Polarion/SCC-11865
SCC-11861 | Prdoukt erweitern auf PTC Mechanik | Lowest |  | Accepted | 44860.4598 | Enhancement Request | relates to: SCC-12107 | SCC_Polarion/SCC-11861
SCC-11745 | Schulungshemen Modul 1 definieren | Lowest | SCC 2.107.0, Sprint 4, Sprint 1, SCC 2.108.0 | In Progress | 44847.652 | User Story | specifies: SCC-6657, is implemented by: SCC-11746, is implemented by: SCC-11748, is implemented by: SCC-11747 | SCC_Polarion/SCC-11745
SCC-11554 | Excel Sheet Berechnung FEM Positionen | Lowest |  | Accepted | 44839.4823 | Enhancement Request |  | SCC_Polarion/SCC-11554
SCC-11488 | Funktionaler Test der Gabelmitte verbessern | Lowest |  | Accepted | 44832.573 | Enhancement Request |  | SCC_Polarion/SCC-11488
SCC-11322 | Panelbilder - Placement Differences | Lowest |  | Accepted | 44817.5878 | Enhancement Request | relates to: SCC-9653 | SCC_Polarion/SCC-11322
SCC-11215 | Anpassen nach erstem Review | Medium |  | Open | 44811.5335 | Task | implements: SCC-10155 | SCC_Polarion/SCC-11215
SCC-11214 | Erstes grobes Review | Medium |  | Open | 44811.5333 | Task | implements: SCC-10155 | SCC_Polarion/SCC-11214
SCC-11212 | Dokument verlinken | Medium |  | Open | 44811.5276 | Task | implements: SCC-10156 | SCC_Polarion/SCC-11212
SCC-11211 | Störmeldeliste Aufräumen | Lowest |  | Accepted | 44811.4896 | Enhancement Request |  | SCC_Polarion/SCC-11211
SCC-11192 | OWL +11 LAM Profinet | Lowest |  | Accepted | 44811.3444 | User Story |  | SCC_Polarion/SCC-11192
SCC-11174 | Visio Darstellung der kompletten Softwarestruktur vom SCC | Lowest |  | Accepted | 44810.3697 | Enhancement Request |  | SCC_Polarion/SCC-11174
SCC-11171 | Anpassen und Freigeben | Medium |  | Open | 44804.908 | Task | implements: SCC-11127 | SCC_Polarion/SCC-11171
SCC-11144 | TuType Aus dem Auftrag muss auf Elementebene einsehbar sein | Lowest |  | Accepted | 44802.4096 | Enhancement Request |  | SCC_Polarion/SCC-11144
SCC-11132 | Panel Erweiterungen Hand mit Kamera und kein Kameraminibild | Lowest |  | Accepted | 44798.6049 | Enhancement Request | relates to: SCC-9653 | SCC_Polarion/SCC-11132
SCC-11129 | GenTele, Generierung Teleaufträge RBG intern | Lowest |  | Accepted | 44798.5884 | Enhancement Request |  | SCC_Polarion/SCC-11129
SCC-11128 | Stoppfunktion | Lowest |  | Accepted | 44798.5858 | Enhancement Request |  | SCC_Polarion/SCC-11128
SCC-11127 | Inforamtion zu Produkteigenschaften | Low | SCC 2.107.0, Sprint 4, Sprint 1, Sprint 2, Sprint 3, SCC 2.108.0 | Accepted | 44798.5817 | User Story | specifies: SCC-2575, is implemented by: SCC-11170, is implemented by: SCC-11171, is implemented by: SCC-11169 | SCC_Polarion/SCC-11127
SCC-11126 | OpTest Symbolisch | Lowest |  | Accepted | 44798.5805 | Enhancement Request | relates to: SCC-9653 | SCC_Polarion/SCC-11126
SCC-11125 | Dynamische Spezialstörungen | Lowest |  | Accepted | 44798.5771 | Enhancement Request |  | SCC_Polarion/SCC-11125
SCC-11116 | Anpassen der IO_Liste_Template | Lowest |  | Assigned to Submitter | 44796.3848 | Enhancement Request |  | SCC_Polarion/SCC-11116
SCC-10884 | Erweiterung Workitem SCC 3827 | Lowest |  | Accepted | 44784.6139 | Enhancement Request | relates to: SCC-9653 | SCC_Polarion/SCC-10884
SCC-10878 | LAM Bild auf Panel überprüfen und anpassen | Medium |  | In Progress | 44771.9724 | Task | relates to: SCC-10875, has follow-up: SCC-10892 | SCC_Polarion/SCC-10878
SCC-10876 | HW Konfiguration überprüfen und anpassen | Medium |  | Open | 44771.9687 | Task | relates to: SCC-10875, has follow-up: SCC-10892 | SCC_Polarion/SCC-10876
SCC-10875 | Nummerierung der Funktionen in Elementbeschreibung sind nicht nach System Numbering Guideline | Medium |  | In Progress | 44771.9648 | Bug Report | is related to: SCC-10873, is related to: SCC-10870, is related to: SCC-10871, is related to: SCC-10878, is related to: SCC-10876, is related to: SCC-10877, is related to: SCC-10872, is related to: SCC-10881, is related to: SCC-10892, is related to: SCC-10869, is related to: SCC-10879, is related to: SCC-10880 | SCC_Polarion/SCC-10875
SCC-10821 | Erstellung eines HMI Stil/Design nach Swisslog Richtlinie | Lowest |  | Accepted | 44769.3301 | Enhancement Request | relates to: SCC-9653 | SCC_Polarion/SCC-10821
SCC-10777 | Verbesserungsvorschlag Kapitel Leistungsabgrenzung | Lowest |  | New | 44755.5569 | Enhancement Request |  | SCC_Polarion/SCC-10777
SCC-10527 | Kapitel Absolutwert-Drehgeber in elm Lastaufnahmemittel erfassen | Lowest |  | Accepted | 44727.6334 | Enhancement Request |  | SCC_Polarion/SCC-10527
SCC-10526 | Joystick: RBG fährt los wenn Analog Karte defekt | Medium |  | In Progress | 44727.3645 | Bug Report |  | SCC_Polarion/SCC-10526
SCC-10522 | Programierrichtlinien: Region in Englisch | Lowest |  | Accepted | 44725.4214 | Enhancement Request |  | SCC_Polarion/SCC-10522
SCC-10521 | Dokument: Projektierung Kommunikation | Lowest |  | Accepted | 44725.419 | Enhancement Request |  | SCC_Polarion/SCC-10521
SCC-10519 | DauerTest, JobCycle Beschreibung | Lowest |  | Accepted | 44725.4121 | Enhancement Request |  | SCC_Polarion/SCC-10519
SCC-10511 | ACP: Number of TU's with info block | Lowest |  | Accepted | 44722.5272 | Enhancement Request | is related to: SCC-10518 | SCC_Polarion/SCC-10511
SCC-10510 | Lösung für Gabelversatz bei doppelief | Lowest |  | Accepted | 44721.7607 | Enhancement Request |  | SCC_Polarion/SCC-10510
SCC-10506 | Vorlage Kundenschulung | Lowest |  | Accepted | 44714.551 | Enhancement Request | relates to: SCC-6657 | SCC_Polarion/SCC-10506
SCC-10441 | Automatisches Update des Copyright Jahres bei Word Export | Lowest |  | Accepted | 44711.4877 | Enhancement Request | is related to: SCC-10335 | SCC_Polarion/SCC-10441
SCC-10437 | Grobkonzept für Erneuerung SW Regler | Lowest |  | Draft | 44710.978 | User Story | specifies: SCC-9633 | SCC_Polarion/SCC-10437
SCC-10436 | Testplan | Lowest |  | Draft | 44710.9758 | User Story | specifies: SCC-9633 | SCC_Polarion/SCC-10436
SCC-10435 | Handbetrieb | Lowest |  | Draft | 44710.9722 | User Story | specifies: SCC-9633 | SCC_Polarion/SCC-10435
SCC-10434 | Positionierbetrieb | Lowest |  | Draft | 44710.9624 | User Story | specifies: SCC-9633 | SCC_Polarion/SCC-10434
SCC-10396 | Antriebskonzept in Elementbeschreibung einpflegen | Lowest |  | Draft | 44706.5754 | User Story |  | SCC_Polarion/SCC-10396
SCC-10359 | HMI Benutzerverwaltung - Konzept | Lowest |  | Accepted | 44705.7 | Enhancement Request | relates to: SCC-9653 | SCC_Polarion/SCC-10359
SCC-10339 | Safety F03_OpStatus Geschwindigkeitswahl übersichtlicher | Lowest |  | Accepted | 44705.6287 | Enhancement Request |  | SCC_Polarion/SCC-10339
SCC-10336 | ElSwrInterface01 tError vom DPRD_DAT | Lowest |  | Accepted | 44705.6131 | Enhancement Request |  | SCC_Polarion/SCC-10336
SCC-10198 | Erweiterung des 2. Kapitels in der SCC Betriebsanleitung | Lowest |  | Accepted | 44698.3924 | Enhancement Request |  | SCC_Polarion/SCC-10198
SCC-10156 | Spezifikation ePlan Vorlage | Lowest |  | Accepted | 44686.6884 | User Story | specifies: SCC-2577, is implemented by: SCC-11212 | SCC_Polarion/SCC-10156
SCC-10155 | Anleitung E-Plan Prozess | Lowest | Sprint 1, Sprint 2, Sprint 3, SCC 2.108.0 | Review | 44686.6794 | User Story | relates to: SCC-2577, is implemented by: SCC-12530, is implemented by: SCC-12531, is related to: SCC-10154, is implemented by: SCC-11213, is implemented by: SCC-11214, is implemented by: SCC-11215 | SCC_Polarion/SCC-10155
SCC-10154 | Anleitung ePlan Macros | Lowest | Sprint 1, Sprint 2, Sprint 3, SCC 2.108.0 | Accepted | 44686.6778 | User Story | relates to: SCC-10155, is implemented by: SCC-12110, is implemented by: SCC-12112, is implemented by: SCC-12111, is implemented by: SCC-12532 | SCC_Polarion/SCC-10154
SCC-9900 | Anpassung Installationsausschreibung SCC | Lowest |  | Accepted | 44683.6738 | Enhancement Request |  | SCC_Polarion/SCC-9900
SCC-9898 | HMI Bezeichnungschilder mit Grafik Vorlage erstellen | Lowest |  | Accepted | 44680.7276 | Enhancement Request | relates to: SCS-23611 | SCC_Polarion/SCC-9898
SCC-9805 | Update Dokumentation für F_override | Lowest |  | Draft | 44678.8038 | User Story |  | SCC_Polarion/SCC-9805
SCC-9797 | HOP Poswerte in Config | Lowest |  | Accepted | 44677.4875 | Enhancement Request |  | SCC_Polarion/SCC-9797
SCC-9796 | HOP Konfig Modular | Lowest |  | Accepted | 44677.4834 | Enhancement Request |  | SCC_Polarion/SCC-9796
SCC-9795 | Einmessen der Trägerhöhen/ Optimieren der Y-Positionen des Lagers | Lowest |  | Accepted | 44677.3952 | Enhancement Request |  | SCC_Polarion/SCC-9795
SCC-9653 | Bedienpanel | Lowest |  | In Progress | 44664.8529 | Epic | is related to: SCC-7958, is related to: SCC-2702, is related to: SCC-6172, is related to: SCC-11126, is related to: SCC-11322, is related to: SCC-11132, is related to: SCC-10884, is related to: SCC-10359, is specified by: SCC-10438, is related to: SCC-10821, is related to: SCC-9635 | SCC_Polarion/SCC-9653
SCC-9633 | SW Regler V2 | Highest |  | In Progress | 44664.6938 | Epic | is related to: SCC-9649, is related to: SCC-9646, is specified by: SCC-10436, is specified by: SCC-10434, is specified by: SCC-10435, is specified by: SCC-10437 | SCC_Polarion/SCC-9633
SCC-9631 | Sichere Kommunikation zu Fremdgewerke | Lowest |  | Accepted | 44664.4652 | Epic | is related to: SCC-9599, is related to: SCC-9603, is related to: SCC-9602, is related to: SCC-9601, is related to: SCC-9600 | SCC_Polarion/SCC-9631
SCC-9603 | Wir brauchen eine SW Beschreibung wie viele Sichere Signale von externen Gewerken verarbeitet werden sollen | Lowest |  | Draft | 44659.998 | User Story | relates to: SCC-9631 | SCC_Polarion/SCC-9603
SCC-9602 | Wir brauchen eine SW Beschreibung wie vereinzelt Sichere Signale von externen Gewerken verarbeitet werden sollen | Lowest |  | Draft | 44659.9976 | User Story | relates to: SCC-9631, is related to: SCC-6688 | SCC_Polarion/SCC-9602
SCC-9601 | Definition wie viele Sicherheitssignale zu anderen Fremdgewerken geteilt werden | Lowest |  | Draft | 44659.9894 | User Story | relates to: SCC-9631, is related to: SCC-9654 | SCC_Polarion/SCC-9601
SCC-9600 | Validierung Austuasch von Sicheren Signalen zu Fremdgewerken | Lowest |  | Draft | 44659.9879 | User Story | relates to: SCC-9631, is related to: SCC-6689 | SCC_Polarion/SCC-9600
SCC-9599 | Definition wie einzelne Sicherheitssignale zu anderen Fremdgewerken geteilt werden | Lowest |  | Draft | 44659.9802 | User Story | relates to: SCC-9631, is related to: SCC-6687 | SCC_Polarion/SCC-9599
SCC-9595 | Hauptschalter verwenden, welcher sich mit Werkzeug in Position ON öffnen lässt | Lowest |  | Draft | 44659.9432 | User Story | is related to: SCC-6675 | SCC_Polarion/SCC-9595
SCC-9594 | Option: Leistungsanpassung über SPOC | Lowest |  | Draft | 44659.9273 | User Story | is related to: SCC-9553 | SCC_Polarion/SCC-9594
SCC-9593 | Option: Leistungsanpassung übers TP | Lowest |  | Draft | 44659.924 | User Story | is related to: SCC-9553 | SCC_Polarion/SCC-9593
SCC-9584 | SW Guidelines um Globalen Konstanten ergänzen | Lowest |  | Assigned to Submitter | 44656.6732 | Enhancement Request |  | SCC_Polarion/SCC-9584
SCC-9580 | Elm. Beschreibung Fahrwerk HW input für DLS | Lowest |  | Accepted | 44655.4694 | Enhancement Request | is related to: SCC-9581 | SCC_Polarion/SCC-9580
SCC-9546 | Anwendung von Reglerinbetriebnahme am Testmodell schulen | Lowest |  | Accepted | 44651.5961 | Enhancement Request |  | SCC_Polarion/SCC-9546
SCC-9530 | Pufferüberwachung und 100% Puffer | Medium |  | Accepted | 44650.4631 | Enhancement Request | relates to: SCC-11883 | SCC_Polarion/SCC-9530
SCC-9523 | Handbücher Produkt | Lowest |  | Draft | 44648.4084 | Epic | is related to: SCC-9902, is specified by: SCC-4889, is specified by: SCC-4890, is specified by: SCC-4891, is related to: SCC-9935, is related to: SCC-9901, is related to: SCC-9903, is specified by: SCC-2318, is specified by: SCC-2319 | SCC_Polarion/SCC-9523
SCC-9357 | State einer Statemachine als Konstanten und nicht als Zahl (Magic Number) | Lowest |  | Accepted | 44630.666 | Enhancement Request |  | SCC_Polarion/SCC-9357
SCC-9229 | Customized Beschreibung/Deckblatt "MM-MoveModul/Spezialmodule" optimieren | Lowest | SCC 2.106.0 | stopped | 44627.361 | User Story | relates to: SCS-24461, is related to: SCC-6594 | SCC_Polarion/SCC-9229
SCC-9226 | SCC According system numbering guideline | Lowest |  | Accepted | 44627.3144 | User Story | specifies: SCC-2577, is implemented by: SCC-9792, is related to: SCC-6167 | SCC_Polarion/SCC-9226
SCC-9223 | Schulungsprojekt auf Masterbasis | Lowest |  | Draft | 44627.3111 | User Story | specifies: SCC-6657, is related to: SCC-2656 | SCC_Polarion/SCC-9223
SCC-9220 | NORM: Zusätzliche Personen auf dem Hubwagen | Lowest |  | Accepted | 44624.7768 | Enhancement Request | relates to: SCC-11883 | SCC_Polarion/SCC-9220
SCC-9218 | NORM: 1840 Vorzone [Lagerkopf OG] | Lowest |  | Accepted | 44624.7676 | Enhancement Request | relates to: SCC-11883 | SCC_Polarion/SCC-9218
SCC-9217 | NORM: 1310 LAM [Lastüberhang] | Lowest |  | Accepted | 44624.7622 | Enhancement Request | relates to: SCC-11883 | SCC_Polarion/SCC-9217
SCC-9214 | NORM: 1010 Bedienstelle | Lowest |  | Accepted | 44624.6773 | Enhancement Request | relates to: SCC-11883, is related to: SCC-7008 | SCC_Polarion/SCC-9214
SCC-9155 | Erweiterung: Anwenderbeschreibung SEW Antriebssysteme mit einem Kapitel zum Thema MoviMot + MoviDriveC | Lowest |  | Accepted | 44613.4508 | Enhancement Request |  | SCC_Polarion/SCC-9155
SCC-7983 | Ausschreibung Installation: Formatabgleich mit SCS | Lowest |  | Draft | 44507.795 | User Story | specifies: SCC-6597 | SCC_Polarion/SCC-7983
SCC-7962 | Template UserStory | Lowest |  | Draft | 44504.772 | User Story |  | SCC_Polarion/SCC-7962
SCC-7958 | Gabelmitte in der Visualisierung anpassen | Medium |  | Accepted | 44504.3896 | Enhancement Request | relates to: SCC-9653 | SCC_Polarion/SCC-7958
SCC-7340 | Daten auf SD-Karte speichern | Medium |  | Accepted | 44469.6015 | Enhancement Request | relates to: SCC-12109, is related to: SCC-6713 | SCC_Polarion/SCC-7340
SCC-7008 | 3. ET200SP fehlersicheres Technologiemodul F-TM Count: | High |  | Accepted | 44438.6976 | Enhancement Request | relates to: SCC-9214 | SCC_Polarion/SCC-7008
SCC-7004 | Komponentenliste SCC | Medium |  | Open | 44421.8334 | Task |  | SCC_Polarion/SCC-7004
SCC-6713 | InitOffset Wert von Laser, nach initialisierung Achse permanent speichern | Highest |  | Accepted | 44384.6056 | Enhancement Request | relates to: SCC-7340, relates to: SCC-12109 | SCC_Polarion/SCC-6713
SCC-6702 | NORM: 1660 Gasse [Zaun mit Zutrittstür] Option Notfall-Schlüsselbox | Highest |  | Accepted | 44371.3713 | Enhancement Request | relates to: SCC-11883 | SCC_Polarion/SCC-6702
SCC-6701 | NORM: Informationen über Instandhaltung, Reparatur und Störungsbeseitigung | Medium |  | Accepted | 44371.3708 | Enhancement Request | relates to: SCC-11883 | SCC_Polarion/SCC-6701
SCC-6700 | NORM: Anleitung für Belastungsprüfung | Medium |  | Accepted | 44371.3702 | Enhancement Request | relates to: SCC-11883 | SCC_Polarion/SCC-6700
SCC-6699 | NORM: Anleitung für Prüfung von Lärm | Medium |  | Accepted | 44371.3698 | Enhancement Request | relates to: SCC-11883 | SCC_Polarion/SCC-6699
SCC-6698 | NORM: Aufzeichnungen der Prüfung von Überlast | Medium |  | Accepted | 44371.3692 | Enhancement Request | relates to: SCC-11883 | SCC_Polarion/SCC-6698
SCC-6697 | NORM: 1340 LAM [Durchschubsicherung] | Medium |  | Accepted | 44371.3686 | Enhancement Request | relates to: SCC-11883 | SCC_Polarion/SCC-6697
SCC-6696 | NORM: 1120 Fahrwerk [Endbegrenzungen] | Medium |  | Accepted | 44371.368 | Enhancement Request | relates to: SCC-11883 | SCC_Polarion/SCC-6696
SCC-6677 | NORM: 1230 Hubwerk [Überlast] | Medium |  | Accepted | 44356.4933 | Enhancement Request | relates to: SCC-11883 | SCC_Polarion/SCC-6677
SCC-6657 | Schulung Produkt | Highest |  | In Progress | 44349.3912 | Epic | is specified by: SCC-9223, is specified by: SCC-1847, is specified by: SCC-1848, is specified by: SCC-6651, is specified by: SCC-6652, is specified by: SCC-6656, is specified by: SCC-6653, is related to: SCC-10506, is specified by: SCC-11745 | SCC_Polarion/SCC-6657
SCC-6656 | Schulungsunterlagen ACM | Lowest |  | Draft | 44349.3907 | User Story | specifies: SCC-6657 | SCC_Polarion/SCC-6656
SCC-6655 | Implement: Produktpräsentation SW | Medium |  | Open | 44349.3904 | Task | implements: SCC-6653 | SCC_Polarion/SCC-6655
SCC-6654 | Implement: Produktpräsentation HW | Medium |  | Open | 44349.3902 | Task | implements: SCC-6653 | SCC_Polarion/SCC-6654
SCC-6653 | Produktpräsentation | Medium |  | Draft | 44349.3899 | User Story | specifies: SCC-6657, is implemented by: SCC-6655, is implemented by: SCC-6654 | SCC_Polarion/SCC-6653
SCC-6652 | Schulungsunterlagen Support | Lowest |  | Draft | 44349.3894 | User Story | specifies: SCC-6657 | SCC_Polarion/SCC-6652
SCC-6651 | Schulungsunterlagen SW-Engineer | Lowest |  | Draft | 44349.3889 | User Story | specifies: SCC-6657 | SCC_Polarion/SCC-6651
SCC-6597 | Ausschreibung Elektroinstallation | High |  | Draft | 44349.3304 | Epic | is specified by: SCC-7979, is specified by: SCC-7983, is specified by: SCC-7980 | SCC_Polarion/SCC-6597
SCC-6531 | LocationRequest | Medium |  | Accepted | 44333.5946 | Enhancement Request |  | SCC_Polarion/SCC-6531
SCC-6385 | NORM: Beschreibung für Testfall Fangbremse | Medium |  | Accepted | 44316.6298 | Enhancement Request | relates to: SCC-11883 | SCC_Polarion/SCC-6385
SCC-6172 | HMI Strukturüberarbeitung | High |  | Accepted | 44277.5773 | Enhancement Request | relates to: SCC-9653 | SCC_Polarion/SCC-6172
SCC-6171 | Option: Condition Monitoring als TP Optionspacket für standard erstellen | Low |  | Accepted | 44277.5574 | Enhancement Request |  | SCC_Polarion/SCC-6171
SCC-6170 | Profinet Devicenamen | Low |  | Accepted | 44274.5601 | Enhancement Request |  | SCC_Polarion/SCC-6170
SCC-4891 | Projektierungs-Handbuch HW | Medium |  | Draft | 44161.424 | User Story | specifies: SCC-9523 | SCC_Polarion/SCC-4891
SCC-4890 | Inbetriebnahme-Handbuch HW | Medium |  | Draft | 44161.4238 | User Story | specifies: SCC-9523 | SCC_Polarion/SCC-4890
SCC-4889 | Handbuch Allgemein | Medium |  | Draft | 44161.423 | User Story | specifies: SCC-9523 | SCC_Polarion/SCC-4889
SCC-4297 | Spezifikation Schleppkette | Low |  | Accepted | 44069.9003 | Enhancement Request |  | SCC_Polarion/SCC-4297
SCC-3919 | Spezifikation_ePlan_Vorlagen | Highest |  | Open | 43973.3078 | Task | implements: SCC-3915 | SCC_Polarion/SCC-3919
SCC-3918 | Anleitung ePlan Macros | Highest |  | Open | 43973.3076 | Task | implements: SCC-3915 | SCC_Polarion/SCC-3918
SCC-3917 | Anleitung ePlan | Highest |  | Open | 43973.3073 | Task | implements: SCC-3915 | SCC_Polarion/SCC-3917
SCC-3527 | Zutrittskonzept über FA mit VW im HRL | Medium |  | Accepted | 43927.6567 | Enhancement Request |  | SCC_Polarion/SCC-3527
SCC-2767 | Produktkatalog: Kapitelanordnung anpassen | Highest |  | Open | 43893.8667 | Task | implements: SCC-2575 | SCC_Polarion/SCC-2767
SCC-2702 | PC-Panels | Highest |  | Accepted | 43888.6167 | Enhancement Request | relates to: SCC-9653 | SCC_Polarion/SCC-2702
SCC-2577 | EPLAN Vorlage | Highest |  | In Progress | 43866.5754 | Epic | is related to: SCC-10155, is specified by: SCC-8040, is specified by: SCC-1842, is specified by: SCC-3915, is specified by: SCC-9226, is specified by: SCC-7521, is specified by: SCC-10433, is specified by: SCC-11180, is specified by: SCC-11193, is specified by: SCC-11206, is specified by: SCC-12525, is specified by: SCC-11175, is specified by: SCC-9897, is specified by: SCC-9598, is specified by: SCC-11190, is specified by: SCC-11185, is specified by: SCC-10429, is specified by: SCC-10430, is specified by: SCC-11191, is specified by: SCC-10428, is specified by: SCC-10432, is specified by: SCC-10431, is specified by: SCC-10156, is related to: SCC-6166 | SCC_Polarion/SCC-2577
SCC-2575 | Produktkatalog | Highest |  | In Progress | 43866.5728 | Epic | is implemented by: SCC-3945, is implemented by: SCC-2770, is implemented by: SCC-2768, is implemented by: SCC-2766, is implemented by: SCC-2769, is implemented by: SCC-2767, is specified by: SCC-11122, is specified by: SCC-11121, is specified by: SCC-11127 | SCC_Polarion/SCC-2575
SCC-2321 | Beschreibung Inbetriebnahme SW | Highest |  | In Progress | 43808.3784 | Task | implements: SCC-2319 | SCC_Polarion/SCC-2321
SCC-2320 | Beschreibung Projektierung SW | Highest |  | In Progress | 43808.3775 | Task | implements: SCC-2318 | SCC_Polarion/SCC-2320
SCC-2319 | Inbetriebnahme-Handbuch SW | Highest |  | Draft | 43808.3763 | User Story | specifies: SCC-9523, is implemented by: SCC-3794, is implemented by: SCC-2321 | SCC_Polarion/SCC-2319
SCC-2318 | Projektierungs-Handbuch SW | Highest |  | Draft | 43808.3761 | User Story | specifies: SCC-9523, is implemented by: SCC-3795, is implemented by: SCC-2320 | SCC_Polarion/SCC-2318

## Polarion (hidden)
Property | Value
New Work Item Type | requirement
New Comments Column | Comments by (.*)
Column | Field
ID | id
Title | title
Severity | severity
Status | status
Planned In | plannedIn
Type | type
Priority | priority
Linked Work Items | linkedWorkItems
_polarion | _polarion
Created | created

## _polarion (hidden)
Type | Label | ID | Field
SCC_Polarion/:Priority | Default | 50.0 | priority
SCC_Polarion/:Priority | Highest | 90.0 | priority
SCC_Polarion/:Priority | High | 70.0 | priority
SCC_Polarion/:Priority | Medium | 50.0 | priority
SCC_Polarion/:Priority | Low | 30.0 | priority
SCC_Polarion/:Priority | Lowest | 10.0 | priority
SCC_Polarion/User Story:Priority | Default | 50.0 | priority
SCC_Polarion/User Story:Priority | Highest | 90.0 | priority
SCC_Polarion/User Story:Priority | High | 70.0 | priority
SCC_Polarion/User Story:Priority | Medium | 50.0 | priority
SCC_Polarion/User Story:Priority | Low | 30.0 | priority
SCC_Polarion/User Story:Priority | Lowest | 10.0 | priority
SCC_Polarion/Technical Documentation:Priority | Default | 50.0 | priority
SCC_Polarion/Technical Documentation:Priority | Highest | 90.0 | priority
SCC_Polarion/Technical Documentation:Priority | High | 70.0 | priority
SCC_Polarion/Technical Documentation:Priority | Medium | 50.0 | priority
SCC_Polarion/Technical Documentation:Priority | Low | 30.0 | priority
SCC_Polarion/Technical Documentation:Priority | Lowest | 10.0 | priority
SCC_Polarion/Bug Report:Priority | Default | 50.0 | priority
SCC_Polarion/Bug Report:Priority | Highest | 90.0 | priority
SCC_Polarion/Bug Report:Priority | High | 70.0 | priority
SCC_Polarion/Bug Report:Priority | Medium | 50.0 | priority
SCC_Polarion/Bug Report:Priority | Low | 30.0 | priority
SCC_Polarion/Bug Report:Priority | Lowest | 10.0 | priority
SCC_Polarion/Defect:Priority | Default | 50.0 | priority
SCC_Polarion/Defect:Priority | Highest | 90.0 | priority
SCC_Polarion/Defect:Priority | High | 70.0 | priority
SCC_Polarion/Defect:Priority | Medium | 50.0 | priority
SCC_Polarion/Defect:Priority | Low | 30.0 | priority
SCC_Polarion/Defect:Priority | Lowest | 10.0 | priority
SCC_Polarion/Epic:Priority | Default | 50.0 | priority
SCC_Polarion/Epic:Priority | Highest | 90.0 | priority
SCC_Polarion/Epic:Priority | High | 70.0 | priority
SCC_Polarion/Epic:Priority | Medium | 50.0 | priority
SCC_Polarion/Epic:Priority | Low | 30.0 | priority
SCC_Polarion/Epic:Priority | Lowest | 10.0 | priority
SCC_Polarion/Enhancement Request:Priority | Default | 50.0 | priority
SCC_Polarion/Enhancement Request:Priority | Highest | 90.0 | priority
SCC_Polarion/Enhancement Request:Priority | High | 70.0 | priority
SCC_Polarion/Enhancement Request:Priority | Medium | 50.0 | priority
SCC_Polarion/Enhancement Request:Priority | Low | 30.0 | priority
SCC_Polarion/Enhancement Request:Priority | Lowest | 10.0 | priority
SCC_Polarion/Heading:Priority | Default | 50.0 | priority
SCC_Polarion/Heading:Priority | Highest | 90.0 | priority
SCC_Polarion/Heading:Priority | High | 70.0 | priority
SCC_Polarion/Heading:Priority | Medium | 50.0 | priority
SCC_Polarion/Heading:Priority | Low | 30.0 | priority
SCC_Polarion/Heading:Priority | Lowest | 10.0 | priority
SCC_Polarion/Task:Priority | Default | 50.0 | priority
SCC_Polarion/Task:Priority | Highest | 90.0 | priority
SCC_Polarion/Task:Priority | High | 70.0 | priority
SCC_Polarion/Task:Priority | Medium | 50.0 | priority
SCC_Polarion/Task:Priority | Low | 30.0 | priority
SCC_Polarion/Task:Priority | Lowest | 10.0 | priority
SCC_Polarion/:Status | New | new | status
SCC_Polarion/:Status | In Progress | inprogress | status
SCC_Polarion/:Status | Reopened | reopened | status
SCC_Polarion/:Status | Closed | closed | status
SCC_Polarion/:Status | Rejected | rejected | status
SCC_Polarion/:Status | Verified as Done | verified-done | status
SCC_Polarion/:Status | Verified as Rejected | verified-rejected | status
SCC_Polarion/:Status | Implemented (project) | project | status
SCC_Polarion/User Story:Status | Draft | draft | status
SCC_Polarion/User Story:Status | Review | review | status
SCC_Polarion/User Story:Status | Accepted | accepted | status
SCC_Polarion/User Story:Status | In Progress | in_progress | status
SCC_Polarion/User Story:Status | Implemented | implemented | status
SCC_Polarion/User Story:Status | Verified | verified | status
SCC_Polarion/User Story:Status | Rejected | rejected | status
SCC_Polarion/Technical Documentation:Status | New | new | status
SCC_Polarion/Technical Documentation:Status | Under Review | under_review | status
SCC_Polarion/Technical Documentation:Status | Implemented | implemented | status
SCC_Polarion/Bug Report:Status | New | new | status
SCC_Polarion/Bug Report:Status | In Progress | inprogress | status
SCC_Polarion/Bug Report:Status | Assigned to Submitter | assigned_to_submitter | status
SCC_Polarion/Bug Report:Status | Closed | closed | status
SCC_Polarion/Bug Report:Status | Rejected | rejected | status
SCC_Polarion/Bug Report:Status | On Hold | onhold | status
SCC_Polarion/Defect:Status | Open | open | status
SCC_Polarion/Defect:Status | In Progress | inprogress | status
SCC_Polarion/Defect:Status | Closed | closed | status
SCC_Polarion/Defect:Status | Rejected | rejected | status
SCC_Polarion/Epic:Status | Draft | draft | status
SCC_Polarion/Epic:Status | Accepted | accepted | status
SCC_Polarion/Epic:Status | In Progress | in_progress | status
SCC_Polarion/Epic:Status | Implemented | implemented | status
SCC_Polarion/Enhancement Request:Status | New | new | status
SCC_Polarion/Enhancement Request:Status | Accepted | accepted | status
SCC_Polarion/Enhancement Request:Status | Assigned to Submitter | assigned_to_submitter | status
SCC_Polarion/Enhancement Request:Status | Rejected | rejected | status
SCC_Polarion/Enhancement Request:Status | Planned | planned | status
SCC_Polarion/Heading:Status | . | open | status
SCC_Polarion/Task:Status | Open | open | status
SCC_Polarion/Task:Status | In Progress | inprogress | status
SCC_Polarion/Task:Status | On Hold | onHold | status
SCC_Polarion/Task:Status | Under Review | under_review | status
SCC_Polarion/Task:Status | Closed | closed | status
SCC_Polarion/Task:Status | Rejected | rejected | status
SCC_Polarion/:Type | User Story | userstory | type
SCC_Polarion/:Type | Task | task | type
SCC_Polarion/:Type | Technical Documentation | technicaldocumentation | type
SCC_Polarion/:Type | Defect | defect | type
SCC_Polarion/:Type | Bug Report | bugreport | type
SCC_Polarion/:Type | Enhancement Request | enhancementrequest | type
SCC_Polarion/:Type | Epic | epic | type
SCC_Polarion/:Type | Heading | heading | type
Work Item | Revision | Checksum | Level | Test Fields Checksum | Read Only
SCC_Polarion/SCC-13359 | 5444230 | f085a60a3c096368549da923699b34486fc65fe1 | 0 |  | 0
SCC_Polarion/SCC-13186 | 5444190 | e93613eba0a7e51ad904b4c727b18d2f36d0e137 | 0 |  | 0
SCC_Polarion/SCC-13185 | 5444190 | c0edd89465fedc862771f85b709a65cbb941584e | 0 |  | 0
SCC_Polarion/SCC-13184 | 5445025 | e789d179ec874e006103896dc767e4a83607b23c | 0 |  | 0
SCC_Polarion/SCC-13183 | 5445025 | 91e85002c3a0fd6126ef3b9327ad9b74585af8d9 | 0 |  | 0
SCC_Polarion/SCC-13182 | 5445025 | 1c0f833c9097635319705442a62d253602ef6a8a | 0 |  | 0
SCC_Polarion/SCC-13181 | 5445025 | a19dcd511011c0c445a5213de8fea4a3f6caa65c | 0 |  | 0
SCC_Polarion/SCC-13180 | 5445025 | 973141a03be369cdb263050319539fdbe67fa516 | 0 |  | 0
SCC_Polarion/SCC-13179 | 5445025 | 617c42d36887ccaa77dede19344fb25590fb5e0e | 0 |  | 0
SCC_Polarion/SCC-13178 | 5445025 | 8fc3256a49835a8112ffd7dfd550d431589d5c94 | 0 |  | 0
SCC_Polarion/SCC-13177 | 5445025 | 095a8bcb81c6d0b48a6472e7ef8aa670c32f6b48 | 0 |  | 0
SCC_Polarion/SCC-13176 | 5445025 | 79781981628af0a2c67f28c8136928ac85c08bc9 | 0 |  | 0
SCC_Polarion/SCC-13175 | 5445025 | af1f358a9a1a1ee38ef35f35e974b47e1964c256 | 0 |  | 0
SCC_Polarion/SCC-13174 | 5445025 | e6ef034212e30d7910555c44052ec79069eeb30c | 0 |  | 0
SCC_Polarion/SCC-13173 | 5445025 | 6c4b496c2c2c051347f1f000fff94966be48131b | 0 |  | 0
SCC_Polarion/SCC-13172 | 5445025 | b6ea10f031abd69b8412e43d3c75779f5d14bc24 | 0 |  | 0
SCC_Polarion/SCC-13171 | 5445025 | d92755fc37bd9ba88c39856c5c21115e22230793 | 0 |  | 0
SCC_Polarion/SCC-13170 | 5445025 | 9ca3d9cafb5c54c53e1492e7f36d4fd610c83037 | 0 |  | 0
SCC_Polarion/SCC-13169 | 5445025 | 446a422f686348173ffa010446fb98daad70fdbc | 0 |  | 0
SCC_Polarion/SCC-13168 | 5445025 | b666279ddf537046d34584fe6f4e2324fe4e934c | 0 |  | 0
SCC_Polarion/SCC-13167 | 5445025 | 354112ab2c7aff8cfdbcf2e5cfa769125ba1494e | 0 |  | 0
SCC_Polarion/SCC-13166 | 5443444 | 2fc0c72ba5fc80950e642965a8a57ea1a1f3849a | 0 |  | 0
SCC_Polarion/SCC-13165 | 5443448 | 1ef425c62ab51b3e3d2d23911dd14ffc588521b8 | 0 |  | 0
SCC_Polarion/SCC-13164 | 5445025 | 18c7070e6e13d8844c13cdc58f94037242393c81 | 0 |  | 0
SCC_Polarion/SCC-13122 | 5445045 | 3ffcaeb299b4f9baef326efbc0ad6a91904f3f2e | 0 |  | 0
SCC_Polarion/SCC-13121 | 5445045 | 64bd779a1de1f866edc23e7f887ca977aa8909df | 0 |  | 0
SCC_Polarion/SCC-13109 | 5445045 | 1e48bca7f86cfd43f9ee884c43a0a39d44c2d268 | 0 |  | 0
SCC_Polarion/SCC-12960 | 5445025 | 466f996364ed0952c81f87218b8f4feb730519b3 | 0 |  | 0
SCC_Polarion/SCC-12959 | 5445025 | fb4be193f8773cb7dab58ed4b3a06f5357d1f4f0 | 0 |  | 0
SCC_Polarion/SCC-12958 | 5445025 | 13fe4db2e88850aa5bc6d80dc35384260d8d872b | 0 |  | 0
SCC_Polarion/SCC-12957 | 5445025 | ac6c3faa3c5488d2e90e1e34cd21ba315e8a358f | 0 |  | 0
SCC_Polarion/SCC-12956 | 5445025 | bfb31051da47fa3329a509d562d368ff945e86ef | 0 |  | 0
SCC_Polarion/SCC-12955 | 5445025 | 7915f5613d6300476aa574e4769dc8c6f0f306d5 | 0 |  | 0
SCC_Polarion/SCC-12954 | 5445025 | 81b8d164c4bef105d0d112b6877b0283dc9f33d7 | 0 |  | 0
SCC_Polarion/SCC-12953 | 5445025 | be23a8c8ca9b8f9fec45ff7b946825078c92acac | 0 |  | 0
SCC_Polarion/SCC-12952 | 5445025 | 562033de01f1126c6d870e4a208fbe5bb31a9f45 | 0 |  | 0
SCC_Polarion/SCC-12725 | 5443439 | ec2b3c3287e1fea16a68299b286b8f3c0935d25c | 0 |  | 0
SCC_Polarion/SCC-12724 | 5445025 | dbeb9f0d69b6c2248ce7314c113e5d4b6449304a | 0 |  | 0
SCC_Polarion/SCC-12723 | 5445045 | 1ff248a83cb639494e7828b94d646d34e14b19b4 | 0 |  | 0
SCC_Polarion/SCC-12709 | 5445045 | 3385ca75ee9fdf77ba699f2e70c85c349dd416a1 | 0 |  | 0
SCC_Polarion/SCC-12708 | 5443439 | 1c123fbc10c66e7c1b14a10fdbd68b9dcb597fa7 | 0 |  | 0
SCC_Polarion/SCC-12707 | 5445045 | 0289508435411a5fa0ad908a2bb46060fb78817f | 0 |  | 0
SCC_Polarion/SCC-12685 | 5443439 | 3afb923a3bd9c6997eb1a1e60fa8b1ad55342772 | 0 |  | 0
SCC_Polarion/SCC-12684 | 5443439 | 5a4e0c84d7f6bc5652b2b0fe6fee8ddfec2f9f15 | 0 |  | 0
SCC_Polarion/SCC-12683 | 5443439 | 603a3921ee6b78cda43901f81ec742629538e907 | 0 |  | 0
SCC_Polarion/SCC-12682 | 5443439 | 99c52436d1733b7d2aeba4140f67870736d6031f | 0 |  | 0
SCC_Polarion/SCC-12681 | 5443439 | eaa8be33f62a7fce1d48af888fd7a5e8f42e4b98 | 0 |  | 0
SCC_Polarion/SCC-12680 | 5443439 | b021d7e793425f63d9a8612cf92296f31e8965ac | 0 |  | 0
SCC_Polarion/SCC-12635 | 5443439 | 47bf87f3589ffc48ea29cc727eea27dd5db99835 | 0 |  | 0
SCC_Polarion/SCC-12634 | 5443439 | c058c08cb0ce8052e2303c9387c49cab2b8791e6 | 0 |  | 0
SCC_Polarion/SCC-12633 | 5444190 | d251427ba3479e1fac3cf9eba9ac24ce0ecdcbcf | 0 |  | 0
SCC_Polarion/SCC-12631 | 5445054 | 4a8a06cd2bc613185c672cd587100a378a118e58 | 0 |  | 0
SCC_Polarion/SCC-12544 | 5444361 | a66af984c89b243905539c64ac9593e8c596f194 | 0 |  | 0
SCC_Polarion/SCC-12543 | 5445054 | 331ed9f306642791ce093a0d7d44a86e93a2cac9 | 0 |  | 0
SCC_Polarion/SCC-12540 | 5444361 | 33e53cb80be40e77c2206abe724db77435905c2a | 0 |  | 0
SCC_Polarion/SCC-12539 | 5445025 | 75036671a314480ab225cd883bf052d709450551 | 0 |  | 0
SCC_Polarion/SCC-12538 | 5445025 | 5593e8106d9df3c9260cdd4c1373462412062bac | 0 |  | 0
SCC_Polarion/SCC-12537 | 5445025 | 6d9369e9384cf12acfc5865523b461cb8b3ae705 | 0 |  | 0
SCC_Polarion/SCC-12536 | 5445025 | bc08116c81f7a40a2ad4af06015cbaae883ee953 | 0 |  | 0
SCC_Polarion/SCC-12535 | 5445025 | fef5628a179ec8d57330e56f938d81ee9c942b1c | 0 |  | 0
SCC_Polarion/SCC-12534 | 5444190 | ab9c15e931b448e211bf287cd9e15715f36785f9 | 0 |  | 0
SCC_Polarion/SCC-12533 | 5444190 | 0112bd52a3b1edff274de0539bc2381303668331 | 0 |  | 0
SCC_Polarion/SCC-12532 | 5444190 | 7b82352a3b44aee81038d396ad94e5676c70a232 | 0 |  | 0
SCC_Polarion/SCC-12531 | 5444190 | ac2947b9d1b9765a40dd10d7abf51b3457aa9af8 | 0 |  | 0
SCC_Polarion/SCC-12530 | 5444190 | 231e8356214922bf453737a7567c8746cd37cd83 | 0 |  | 0
SCC_Polarion/SCC-12529 | 5444390 | f329636d5cb51f53a5c39edfcd21dc35cfb20c46 | 0 |  | 0
SCC_Polarion/SCC-12528 | 5444190 | 36768bcd50cc8d1b75d3c7cf73989d0817afa0b8 | 0 |  | 0
SCC_Polarion/SCC-12527 | 5444190 | 1b2ca5be4c869576552984d0c69601d20b24c993 | 0 |  | 0
SCC_Polarion/SCC-12526 | 5444190 | f1a6d70477b33d9a16df35140eaab7c6d0d48292 | 0 |  | 0
SCC_Polarion/SCC-12525 | 5444190 | 7bcff4fdf88bc3f0df0c391d119ced7196a962f8 | 0 |  | 0
SCC_Polarion/SCC-12517 | 5445054 | bfcde7130d59e8f5f45347938ce90f5f2c2cbf17 | 0 |  | 0
SCC_Polarion/SCC-12516 | 5445054 | c51f02bace80066e85d8ddde02a655a0ddc2f11b | 0 |  | 0
SCC_Polarion/SCC-12515 | 5445054 | 2697e5e42964d44270719147aa929ea351c7d667 | 0 |  | 0
SCC_Polarion/SCC-12514 | 5445054 | f2ea026aae78b8ab08f4422c290d3f8e01d4c861 | 0 |  | 0
SCC_Polarion/SCC-12512 | 5445054 | 9ade00428d1a26959781a2f2cea810ac741c4e13 | 0 |  | 0
SCC_Polarion/SCC-12511 | 5443439 | 67a5b63b2b3a7927e2f666cc2edb1689af108643 | 0 |  | 0
SCC_Polarion/SCC-12510 | 5445054 | 6172e01120df40caae25a40e94cb48876d165eaf | 0 |  | 0
SCC_Polarion/SCC-12509 | 5444390 | e220e819e9aeb896f569434c6fec8f5d759650dd | 0 |  | 0
SCC_Polarion/SCC-12508 | 5444390 | a5887f973987a5f2fc2a9f17be0bd3f987b37472 | 0 |  | 0
SCC_Polarion/SCC-12498 | 5444390 | d67a044eaf94075562a43ba9413bed4b9c64f481 | 0 |  | 0
SCC_Polarion/SCC-12448 | 5444390 | e2e6479c6c91dc5824f84956967f5005519da76a | 0 |  | 0
SCC_Polarion/SCC-12379 | 5445054 | b48b4266b4798ca8516ee52338cdde60ae6918f7 | 0 |  | 0
SCC_Polarion/SCC-12378 | 5445054 | f29f04538369a127a6ad8054627a9bb913494c76 | 0 |  | 0
SCC_Polarion/SCC-12377 | 5445054 | ac32957d91f8438fd54cc79a6a2ee2dfff81255f | 0 |  | 0
SCC_Polarion/SCC-12376 | 5444306 | 34d0bddd0eb84525d35c41b881aeb0264bc2ee90 | 0 |  | 0
SCC_Polarion/SCC-12375 | 5445054 | dfa84351b8831c8161bff365d019dbbd1dc9d964 | 0 |  | 0
SCC_Polarion/SCC-12374 | 5445054 | a5dcd41c8a78361f7287715b6681ac9c3d73c9e6 | 0 |  | 0
SCC_Polarion/SCC-12373 | 5445054 | e7cca40e8a81e3ddacc71a8e91baf2d5ee506687 | 0 |  | 0
SCC_Polarion/SCC-12372 | 5444306 | 16cbb4c7b22168104c017c2294e9f1a90a2e7595 | 0 |  | 0
SCC_Polarion/SCC-12371 | 5444190 | 87962aaf39ccf04fd07ffc05f9ba0181415aec1c | 0 |  | 0
SCC_Polarion/SCC-12370 | 5444308 | 765e42348ae81861524913f8b19523d9bb4ce5ae | 0 |  | 0
SCC_Polarion/SCC-12368 | 5444310 | 36bdaa8be9ce1b3c8e475c187ff20a195de1a7c2 | 0 |  | 0
SCC_Polarion/SCC-12367 | 5444190 | 3631056eefddb0e50974dd57447d2110c6a17170 | 0 |  | 0
SCC_Polarion/SCC-12366 | 5444190 | 3e6e6dd2f0626237c82ea88399d769baf4314cc7 | 0 |  | 0
SCC_Polarion/SCC-12364 | 5444190 | 220443705ea63b492b3b079b4f782dd28993db4b | 0 |  | 0
SCC_Polarion/SCC-12363 | 5444190 | e918e38cd57454aca057fe3d43e398d92b028fa5 | 0 |  | 0
SCC_Polarion/SCC-12362 | 5444190 | 724a58bb976e3edf212a92ca22eed8415a0aca3c | 0 |  | 0
SCC_Polarion/SCC-12360 | 5444190 | f6276559f706eb527309fe04fe52350847d5bde0 | 0 |  | 0
SCC_Polarion/SCC-12356 | 5444220 | 51ea2e27147e68d80d23524634d1f59121eb82ad | 0 |  | 0
SCC_Polarion/SCC-12355 | 5445054 | a8d70a76488444b07fde1fc53dd4bfbf686ff9a8 | 0 |  | 0
SCC_Polarion/SCC-12354 | 5445054 | f3e9b19228d0b601ccf4e7496f8497fb13e6a1c0 | 0 |  | 0
SCC_Polarion/SCC-12112 | 5444190 | 0bf44d85caf3c9225752e2d20bc681be5162a58e | 0 |  | 0
SCC_Polarion/SCC-12111 | 5444190 | fc9bce6e3ff27b68cb792a32abb332206e8e66a2 | 0 |  | 0
SCC_Polarion/SCC-12110 | 5444190 | e39aadac1efa5139bd82b0e97f1dd14fbdce63d1 | 0 |  | 0
SCC_Polarion/SCC-12109 | 5445025 | f592d85d1ecf29c1d03d90cf3c30fd541564fdc0 | 0 |  | 0
SCC_Polarion/SCC-12108 | 5445054 | 5cdcdd63cd7da4b1dab95cc0c5191b1c5c6cb99f | 0 |  | 0
SCC_Polarion/SCC-12107 | 5445054 | 79896935a662e3f2d17756fcabf5e0d3c37958b2 | 0 |  | 0
SCC_Polarion/SCC-11883 | 5445025 | 021a645cb7b1fdb28bb62b95d1fd249a9c32f727 | 0 |  | 0
SCC_Polarion/SCC-11865 | 5445054 | b93a67f7e6f064628ac35e2b528320d6e6ad1202 | 0 |  | 0
SCC_Polarion/SCC-11861 | 5445054 | b672da7e18c9fbfad7a50dfb96ed016b1073c801 | 0 |  | 0
SCC_Polarion/SCC-11745 | 5445054 | 68f6fe49349c6510faa5a6ccebd70e3114a794fe | 0 |  | 0
SCC_Polarion/SCC-11554 | 5445054 | 9081a5f8b601be8e40ac0a9d9d5d8959a1a2e304 | 0 |  | 0
SCC_Polarion/SCC-11488 | 5445054 | 2136ae9769a835e077655b51ce23b6ba2b30d626 | 0 |  | 0
SCC_Polarion/SCC-11322 | 5445054 | 7ea8cb9d085ffae7a9bb4e85edafd4ec4aa8b311 | 0 |  | 0
SCC_Polarion/SCC-11215 | 5444190 | 91e543eb6fc3707b66be2ad5c0b9a24fdaaf94ad | 0 |  | 0
SCC_Polarion/SCC-11214 | 5444190 | 0e8a641c64a17daa177a08c660d4a657217cde3e | 0 |  | 0
SCC_Polarion/SCC-11212 | 5445054 | d352aeb464464bda5cb37187fed98c2a44440d7f | 0 |  | 0
SCC_Polarion/SCC-11211 | 5445054 | 161a5c12acb1daf29d67a83268a36f5986742468 | 0 |  | 0
SCC_Polarion/SCC-11192 | 5445054 | a4e51caadcaeaf8698cb52846418771e7143d9a6 | 0 |  | 0
SCC_Polarion/SCC-11174 | 5445054 | 9da216bc56b39468e54af722bfe265f1b8ee1df7 | 0 |  | 0
SCC_Polarion/SCC-11171 | 5444190 | 0f61fc6304085b1d691fae3c01b8935cfbc7a58e | 0 |  | 0
SCC_Polarion/SCC-11144 | 5445054 | 8d0cb4d4a9374a43e2adad3484cad7970ceefb05 | 0 |  | 0
SCC_Polarion/SCC-11132 | 5445054 | 48cfd6ae97cb30c268c29da3a8d08359e5d0a4a2 | 0 |  | 0
SCC_Polarion/SCC-11129 | 5445054 | 7f9e9709845bcd02742687968acf45ed707b3469 | 0 |  | 0
SCC_Polarion/SCC-11128 | 5445054 | 8ccdfe1cdb5fa77702cfe2090727d2de90a29650 | 0 |  | 0
SCC_Polarion/SCC-11127 | 5443471 | 371b6d1725edb22fdfcd2dbfed127862346f26a2 | 0 |  | 0
SCC_Polarion/SCC-11126 | 5445054 | bb1c02186a82c4ef4a87fb86a107343ecbf390f2 | 0 |  | 0
SCC_Polarion/SCC-11125 | 5445054 | b87e55d6c5daab6c761c3e49774a112ad09acb82 | 0 |  | 0
SCC_Polarion/SCC-11116 | 5445054 | b40cafe308b3a18167644b48715aa9642a75b7a5 | 0 |  | 0
SCC_Polarion/SCC-10884 | 5445054 | 26b8b9714cced256c22fae4958434dfb59b82d63 | 0 |  | 0
SCC_Polarion/SCC-10878 | 5444230 | 0b1d0c0934b0e9d73c6f0b742462f9d47d5300eb | 0 |  | 0
SCC_Polarion/SCC-10876 | 5444230 | c3e0e8778f412c8b4384880c87ca595d23771404 | 0 |  | 0
SCC_Polarion/SCC-10875 | 5443439 | 9679daf0a6b319b9ca6369b6ce63977ad8c5a304 | 0 |  | 0
SCC_Polarion/SCC-10821 | 5445054 | 41891ee5d9d48f07037923aa9c884c943352c147 | 0 |  | 0
SCC_Polarion/SCC-10777 | 5445054 | 8c53d32e38adb525cdf9cba178b0ac9d39dfdc4a | 0 |  | 0
SCC_Polarion/SCC-10527 | 5445054 | 87d5a85fd90cca653877df1a17383951bf31ccd5 | 0 |  | 0
SCC_Polarion/SCC-10526 | 5444390 | 64a8fe6293abbda38e809eb718b76cd4b56ef791 | 0 |  | 0
SCC_Polarion/SCC-10522 | 5445054 | 350e345c1c598797809d74edf1391f0cf07b586f | 0 |  | 0
SCC_Polarion/SCC-10521 | 5443869 | 6affbf1bf54130ffd3b780f0207d5b667dfebdf8 | 0 |  | 0
SCC_Polarion/SCC-10519 | 5445054 | c4151bb9d0001f89876333a041c2bcf6c2cf2311 | 0 |  | 0
SCC_Polarion/SCC-10511 | 5445054 | 51c23dc0a7e9aed848a639ff97d01e02c7fc26ea | 0 |  | 0
SCC_Polarion/SCC-10510 | 5445054 | 3cde8f95d9d8cac104270dc30f16583b977cf51f | 0 |  | 0
SCC_Polarion/SCC-10506 | 5445054 | 6ea46921bc96b11423e8711a1118f79c31c7c2f8 | 0 |  | 0
SCC_Polarion/SCC-10441 | 5445054 | 815de9d2b4873aa058d0e7e6c666e82f3cddc382 | 0 |  | 0
SCC_Polarion/SCC-10437 | 5445054 | 34e5b906c6786d3b9100919882bd5bf6f22f62e5 | 0 |  | 0
SCC_Polarion/SCC-10436 | 5445054 | b49f8f3950bafa1d98f34ba2d52997a4b72f1713 | 0 |  | 0
SCC_Polarion/SCC-10435 | 5445054 | d0756ce8703d72e3b289d02bca9c4d419591ee2f | 0 |  | 0
SCC_Polarion/SCC-10434 | 5445054 | 4d9a2dcfb4759c4fff534f4bc11b39a29cb7434e | 0 |  | 0
SCC_Polarion/SCC-10396 | 5445054 | 060867b6863f530d7aafe7f3c5a1ef741c17695f | 0 |  | 0
SCC_Polarion/SCC-10359 | 5445054 | 79856f62f67928ea0b38a700dcbaac6740e89db8 | 0 |  | 0
SCC_Polarion/SCC-10339 | 5445054 | 819bf01e252cbc454f1311b1873c4675fc37242a | 0 |  | 0
SCC_Polarion/SCC-10336 | 5445054 | 9fcffd3a1dce5d7f44660c876200d15bccba738a | 0 |  | 0
SCC_Polarion/SCC-10198 | 5445054 | 3423cdcb2744ae541a06c93d65b89a1556ee742a | 0 |  | 0
SCC_Polarion/SCC-10156 | 5445054 | 9c1195fd7dbc6452c0cc6d0c64cc1918173e461b | 0 |  | 0
SCC_Polarion/SCC-10155 | 5444190 | c10d90cf3c44301383eb2b5b85c2c17e5efba87e | 0 |  | 0
SCC_Polarion/SCC-10154 | 5444190 | adf2e521c3da72adb5bf73c2bf537a9ca66330ed | 0 |  | 0
SCC_Polarion/SCC-9900 | 5445054 | c6c098b3f60325479840322aae4caf0a2e985113 | 0 |  | 0
SCC_Polarion/SCC-9898 | 5445054 | e91cde85ee8b18f3f53516395f33455605bb2656 | 0 |  | 0
SCC_Polarion/SCC-9805 | 5445054 | ea429b3c38360869ab2a8059c22854ca3be54e49 | 0 |  | 0
SCC_Polarion/SCC-9797 | 5445054 | e895bc03aa9cb40ccd91cfe947277f42dc3029d5 | 0 |  | 0
SCC_Polarion/SCC-9796 | 5445054 | 9f302f047ee319d890f76af19ed02d521374919b | 0 |  | 0
SCC_Polarion/SCC-9795 | 5445054 | 16fcfda07ba2375840031b678216d17ded99b8a0 | 0 |  | 0
SCC_Polarion/SCC-9653 | 5445054 | 7aaf27a7b8257d934b710ce330758c76a0eebdf1 | 0 |  | 0
SCC_Polarion/SCC-9633 | 5445054 | 764724f6cfb744477deabc4430e90d9825b7878b | 0 |  | 0
SCC_Polarion/SCC-9631 | 5445054 | 89cd0806efde83e05b082d9b0d0f97d8ed4d2529 | 0 |  | 0
SCC_Polarion/SCC-9603 | 5445054 | 2e9b66018ad9568db7d762875b46f52a2d21da39 | 0 |  | 0
SCC_Polarion/SCC-9602 | 5445054 | 790f61fa89e51ffa8376d901df6910bbec721b75 | 0 |  | 0
SCC_Polarion/SCC-9601 | 5445054 | 9075f05fe04364ff1504c51e24ea05e3aa8bbc69 | 0 |  | 0
SCC_Polarion/SCC-9600 | 5445054 | d17ebc7c522985e064eaac66aea32ca84e09dc09 | 0 |  | 0
SCC_Polarion/SCC-9599 | 5445054 | 74fb1801b2f85fe905c61bf1757b28b53bbd66fd | 0 |  | 0
SCC_Polarion/SCC-9595 | 5445054 | 7ed336c88ab026b81907778acef4b7aeb3610747 | 0 |  | 0
SCC_Polarion/SCC-9594 | 5445054 | d46ddd56b3fde975b5654425af7f627382bd2b50 | 0 |  | 0
SCC_Polarion/SCC-9593 | 5445054 | 4d3bf7f223d6c7a57f538cb2e74e93bffa2e4289 | 0 |  | 0
SCC_Polarion/SCC-9584 | 5445054 | 75b827306a3da1c80a1fdc4d712f72d2ddeaf1a4 | 0 |  | 0
SCC_Polarion/SCC-9580 | 5445054 | 54f829fff3d81c37a3b53c394da11711a9b17379 | 0 |  | 0
SCC_Polarion/SCC-9546 | 5445054 | 0f2a3b0f68bb8f043d42109719f47a818376d2f2 | 0 |  | 0
SCC_Polarion/SCC-9530 | 5445054 | 0f65eb5cf6c8603f6454c44a8b85ec608ccaac79 | 0 |  | 0
SCC_Polarion/SCC-9523 | 5445054 | f194499296a57bd0bcb7b6b9e750dbdd58858860 | 0 |  | 0
SCC_Polarion/SCC-9357 | 5445054 | e740ddaaf6dbd15cc1988a932ca78a859cdd2aac | 0 |  | 0
SCC_Polarion/SCC-9229 | 5445054 | c7acad5732f7d11ac28fc7bd0921e946369ed8e6 | 0 |  | 0
SCC_Polarion/SCC-9226 | 5445054 | d5ce754574356718991c46f7776f5ed1739beeab | 0 |  | 0
SCC_Polarion/SCC-9223 | 5445054 | ab0012c02b6d938970bf2d6cf88ca3e1693c73bd | 0 |  | 0
SCC_Polarion/SCC-9220 | 5445054 | b5ff1fcbba64c44f39b32b7cfccf2842090f450e | 0 |  | 0
SCC_Polarion/SCC-9218 | 5445054 | dc39868b71009933b7b468218fca66428375afea | 0 |  | 0
SCC_Polarion/SCC-9217 | 5445054 | 8f978b2c23684dfedd75f06857ace8d9c5ad2fde | 0 |  | 0
SCC_Polarion/SCC-9214 | 5445054 | b9e8b56b49aa6ca70686df0cdab1fd217ed86937 | 0 |  | 0
SCC_Polarion/SCC-9155 | 5445054 | a5535e5f326803b4cbf41530344b2d5832d56b7f | 0 |  | 0
SCC_Polarion/SCC-7983 | 5445054 | 9c48aa89e57081e4eff985ac216508c70d84f7b4 | 0 |  | 0
SCC_Polarion/SCC-7962 | 5445054 | 99380da056213deb5ce705a95996936f33c5ed56 | 0 |  | 0
SCC_Polarion/SCC-7958 | 5445054 | 6c020220a1e61992283e287f71afedd3044b4e09 | 0 |  | 0
SCC_Polarion/SCC-7340 | 5445054 | 99deb9d9b6a2b837b5720eb34d3cfdd9cb6fc722 | 0 |  | 0
SCC_Polarion/SCC-7008 | 5445054 | ed3d76451a85cb85309258e153e870e454309390 | 0 |  | 0
SCC_Polarion/SCC-7004 | 5445054 | 93d41af1b48a9483f3d1fa1ea4d55f91ee915619 | 0 |  | 0
SCC_Polarion/SCC-6713 | 5445054 | eac17b727d0f80cdf73480f89d8439b0b7796083 | 0 |  | 0
SCC_Polarion/SCC-6702 | 5445054 | 082914fc12446655e3c417968586c127b47b2bdb | 0 |  | 0
SCC_Polarion/SCC-6701 | 5445054 | 067781b2e0445957c1577def776230fca00cf589 | 0 |  | 0
SCC_Polarion/SCC-6700 | 5443438 | 3234ce5b452c45e2e0f2b66129edc266c198030a | 0 |  | 0
SCC_Polarion/SCC-6699 | 5445054 | f5f1b3d731eaaf2ee6bdf48818170ae235a245c9 | 0 |  | 0
SCC_Polarion/SCC-6698 | 5445054 | ecd1095af497b9d93c0b10da3a20a463a9ea63b7 | 0 |  | 0
SCC_Polarion/SCC-6697 | 5445054 | 44cf97852c79f23317af8ade00cc094443a227da | 0 |  | 0
SCC_Polarion/SCC-6696 | 5445054 | 63bd496058b74c29eaaaaeb706e30ccfb275839d | 0 |  | 0
SCC_Polarion/SCC-6677 | 5445054 | 1f3502e3a561a3a59d0923dad70214c58f468a89 | 0 |  | 0
SCC_Polarion/SCC-6657 | 5445054 | d1dbbb66dd1d9e43b7aaf6e0ec17bdeed2dc4274 | 0 |  | 0
SCC_Polarion/SCC-6656 | 5445054 | f7597d07ac927661e257064bf0593108421f5289 | 0 |  | 0
SCC_Polarion/SCC-6655 | 5445054 | c7bdb3c18c2e6fa9b95a72a7018b2bb6c60a7de2 | 0 |  | 0
SCC_Polarion/SCC-6654 | 5445054 | eddbfe53b2a186305485d91c5bf2c2cc1188fcae | 0 |  | 0
SCC_Polarion/SCC-6653 | 5445054 | 315dcc6b5f9d1d8eeca25005087b538c7bc1ddc9 | 0 |  | 0
SCC_Polarion/SCC-6652 | 5445054 | 7af9cd4a2b00223a7b6501a66b7bc383cf5087ce | 0 |  | 0
SCC_Polarion/SCC-6651 | 5445054 | f060ecbeeb743858f540435319f1aaf6f62b5e41 | 0 |  | 0
SCC_Polarion/SCC-6597 | 5445054 | 862a4628bb64604ecba434e71bf6e74dcb255265 | 0 |  | 0
SCC_Polarion/SCC-6531 | 5445054 | 539fa62aee4523b6c7b8c1a2d8fb4b1d9f7ae660 | 0 |  | 0
SCC_Polarion/SCC-6385 | 5445054 | 598eef1b41c1392dd30fc78bd9003563a406c7e4 | 0 |  | 0
SCC_Polarion/SCC-6172 | 5443438 | 1395d172785803ee233348696f995a1b6ccc7e8d | 0 |  | 0
SCC_Polarion/SCC-6171 | 5445054 | 77fc5ddb9dd050d65beb68b82d842955c0dad6e7 | 0 |  | 0
SCC_Polarion/SCC-6170 | 5445054 | 6b33b4375384d85e23a58e9c088bfa57e088edf9 | 0 |  | 0
SCC_Polarion/SCC-4891 | 5445054 | 97fb5b7034d4844da06e135affe57a164cf8f5e3 | 0 |  | 0
SCC_Polarion/SCC-4890 | 5445054 | 9a6b683968bb869000d70ebe12407182f5e6c6a1 | 0 |  | 0
SCC_Polarion/SCC-4889 | 5445054 | 100b9ada0c3f2d277c813b6900045848c06f8d7b | 0 |  | 0
SCC_Polarion/SCC-4297 | 5445054 | a6b4c354fbfa1b0dd2343d55a0bfb79482081dbb | 0 |  | 0
SCC_Polarion/SCC-3919 | 5445054 | 6ed5ae1657dc2b3643da8fe1603859b9f5234d48 | 0 |  | 0
SCC_Polarion/SCC-3918 | 5445054 | 773936ce92dee593b837e61a0917207b7d195f99 | 0 |  | 0
SCC_Polarion/SCC-3917 | 5445054 | 7ff4896a04daa70d1968df4f0849748de0db63e0 | 0 |  | 0
SCC_Polarion/SCC-3527 | 5445054 | ff5ef8d4197db0659019cc4dbc0655a2fad64971 | 0 |  | 0
SCC_Polarion/SCC-2767 | 5445054 | c2f660d7df2c5501475c10e34de0c4fa03004269 | 0 |  | 0
SCC_Polarion/SCC-2702 | 5445054 | 207111c555835e4edb433b282eb9e803cab38b5e | 0 |  | 0
SCC_Polarion/SCC-2577 | 5445025 | 614e18012d096bb1e2884fbae389555abee2ecda | 0 |  | 0
SCC_Polarion/SCC-2575 | 5445054 | 72ff984eaddc95ebcc22735a63c9239a8ce37458 | 0 |  | 0
SCC_Polarion/SCC-2321 | 5445054 | dd0cec4e628c65d414de75ff31563ec5a6376312 | 0 |  | 0
SCC_Polarion/SCC-2320 | 5445054 | deddd4d8cbb354b10e5761dddea560157eee4be1 | 0 |  | 0
SCC_Polarion/SCC-2319 | 5445054 | b0a8d4f60d4d8578286e18515bc870a319368fb7 | 0 |  | 0
SCC_Polarion/SCC-2318 | 5445054 | d29583250c44766b051d3d40ae09caa6d371eab7 | 0 |  | 0
SCC_Polarion/SCC-1871 | 5445025 | 0c6f01bcc2e03f18752200a99e789fb3dcb1377c | 0 |  | 0
SCC_Polarion/SCC-1848 | 5445054 | 0be7b746a064f565f093a81202259e9a1f51a0de | 0 |  | 0
SCC_Polarion/SCC-1847 | 5445054 | a0f02cff89c03cb7fc321350f4a951a843ae16a0 | 0 |  | 0
SCC_Polarion/SCC-33 | 5445023 | 6e0a43f81c56c081eabc47a9b154768fa78f2730 | 0 |  | 0
Property | Value
project.id | SCC_Polarion
testRun | false
module.location
allowDocumentStructureChanges | false
editableFields